CONCEPT NOTE

TISA INTER-UNIVERSITY

ICT CHALLENGE 2027

Prepared by

Aine Mbabazi Khuzaifah

Vice President, TISA — UICT

Presented to: The Executive Board, TISA — UICT

Date: [Insert Date]

Status: For Discussion and Approval

Table of Contents

1. Executive Summary	3

2. Background and Rationale	3

3. Vision and Mission	3

4. What Makes This Challenge Different	4

5. Objectives	4

6. Proposed Task Force	4

7. Competition Format	5

8. Timeline	6

9. Budget Overview	6

10. Expected Outcomes	7

11. Risks and Mitigation	7

12. What We Are Asking From the Executive Board	7

13. Conclusion	8

Next Steps After Approval	9

# 1. Executive Summary

The TISA Inter-University ICT Challenge 2027 is a national competition that will bring together university students from across Uganda to build deployable ICT solutions for real Ugandan problems.

Unlike existing competitions that are led by a single sector, this challenge will be co-owned by students, government, and private industry. It will be hosted by TISA at UICT and will run from October 2026 to December 2027, with the main event in August 2027.

The challenge is designed to:

- Position TISA as a national leader in student innovation.

- Attract funding and partnerships that benefit the entire association.

- Produce real solutions that are deployed to solve real problems.

- Create opportunities for TISA members — internships, mentorship, jobs, and skills.

# 2. Background and Rationale

Uganda's ICT innovation ecosystem is growing, but it remains fragmented. Several competitions already exist:

| Competition | Organizer | Focus | Limitation |
| --- | --- | --- | --- |
| Huawei ICT Competition | Huawei (private) | Network, Cloud, Computing, Innovation | Corporate-led; focused on Huawei technologies |
| AIFest Inter-University Hackathon | GDG Makerere (student-led) | AI Agents for Uganda | Student-led but limited to AI |
| UCC Communications Testbed Hackathon | UCC (government) | Child Online Protection | Government-led; single theme |
| Bank of Uganda Hackathon | Bank of Uganda (government) | Digital solutions | Government-led; short duration |
| UNACU National ICT Contest | UNACU (non-profit) | Social, environmental, health problems | Non-profit-led; limited visibility |

The gap: No existing competition is truly co-owned by students, government, and private industry. No existing competition guarantees that winning solutions are deployed. And no existing competition is hosted by a student association.

TISA is uniquely positioned to fill this gap.

# 3. Vision and Mission

## Vision

To make TISA the leading student-led innovation hub in Uganda, connecting students, government, and industry to build technology that solves real problems.

## Mission

To organize an annual inter-university ICT challenge that:

- Brings together students from all Ugandan universities.

- Partners with government and private sector organizations.

- Produces deployable ICT solutions for Uganda's biggest challenges.

- Creates lasting opportunities for TISA members.

# 4. What Makes This Challenge Different

| Feature | Existing Competitions | TISA Inter-University ICT Challenge |
| --- | --- | --- |
| Ownership | Single sector (corporate, government, or student) | Tri-sector: students + government + private sector |
| Focus | Specific technology or theme | Any technology, any Ugandan problem |
| Duration | Weekend or a few weeks | Year-long program with mentorship |
| Outcome | Prizes only | Deployment of winning solutions |
| Host | Company, government agency, or NGO | Student association (TISA) |
| Legacy | Event ends | Alumni network, incubation, annual edition |

# 5. Objectives

- To organize Uganda's first tri-sector inter-university ICT challenge.

- To attract at least 10 university teams from across Uganda.

- To secure partnerships with at least 5 government and private sector organizations.

- To deploy at least 3 winning solutions with partner organizations.

- To position TISA as a national leader in student innovation.

- To create internships, mentorships, and job opportunities for TISA members.

- To generate funding and in-kind support for TISA's long-term sustainability.

# 6. Proposed Task Force

To execute this initiative, I propose a dedicated task force drawn from the TISA Executive Board and general membership. The following members are proposed:

| Role | Name | Responsibility |
| --- | --- | --- |
| Project Lead | Aine Mbabazi Khuzaifah (Vice President) | Overall coordination, partner outreach, reporting to Executive Board |
| President | Waasswa Elwin | Strategic oversight, high-level partner meetings, government liaison |
| Publicity Secretary | Phionah Wuafi | Branding, social media, campus tours, media coverage, communications |
| Speaker | Wambi Benard | Rules and governance, judging process, code of conduct, dispute resolution |
| Additional Member (co-opted) | [To be nominated] | Logistics, budgeting, event management |
| Additional Member (co-opted) | [To be nominated] | Mentor recruitment, participant support, university liaison |

NOTE Additional members may be co-opted from the general membership based on skills and availability. The task force will report to the Executive Board monthly.

# 7. Competition Format

## 7.1 Eligibility

- Open to all registered students of Ugandan universities.

- Teams of 2–5 members.

- Any discipline (not just ICT students).

- At least one member must be a TISA member (for TISA members to benefit directly).

## 7.2 Tracks

Teams will choose one of the following tracks:

- Health – Digital health solutions, telemedicine, health records.

- Agriculture – Farmer support, supply chain, market access.

- Education – E-learning, teacher support, student assessment.

- Governance – Civic engagement, transparency, public service delivery.

- Fintech – Financial inclusion, mobile money, savings, credit.

- Open Track – Any other real Ugandan problem.

## 7.3 Judging Criteria

- Innovation – Is the solution new or significantly better?

- Feasibility – Can it be built and deployed?

- Impact – Does it solve a real problem for real people?

- Scalability – Can it grow beyond the pilot?

- Team – Does the team have the skills and commitment?

## 7.4 Prizes

- Cash prizes for top 3 teams (amount depends on funding).

- Incubation support for winning teams.

- Internships with partner companies.

- Deployment contracts with partner organizations.

- Certificates and recognition for all finalists.

# 8. Timeline

| Phase | Period | Key Activities |
| --- | --- | --- |
| Phase 1: Foundation | Oct – Dec 2026 | Concept approval, task force formation, partner mapping, concept note finalization |
| Phase 2: Partnership & Planning | Jan – Mar 2027 | MOUs with anchor partners, funding secured, rulebook finalized, registration launched |
| Phase 3: Mobilization | Apr – Jun 2027 | Campus tours, training workshops, team formation, mentor recruitment, preliminary rounds |
| Phase 4: Competition | Jul – Aug 2027 | Pre-event bootcamp, main event week, demo day, award ceremony |
| Phase 5: Legacy | Sep – Dec 2027 | Deployment of winning solutions, alumni network, impact report, planning for 2028 |

Main Event: August 2027 (exact dates to be confirmed)

# 9. Budget Overview

| Item | Estimated Cost (UGX) | Notes |
| --- | --- | --- |
| Venue | 5,000,000 | UICT or partner venue |
| Catering | 8,000,000 | For finalists, judges, guests |
| Prizes | 15,000,000 | Cash prizes for top 3 teams |
| Transport & Accommodation | 10,000,000 | For finalists from upcountry universities |
| Marketing & Communications | 5,000,000 | Branding, social media, campus tours |
| Tech Infrastructure | 4,000,000 | Wi-Fi, power, projectors |
| Admin & Logistics | 3,000,000 | Printing, materials, misc. |
| Total | 50,000,000 | To be covered by partners and sponsors |

NOTE TISA is not expected to fund this from its own budget. The task force will secure funding from government, private sector, and development partners. A minimal viable event can be run with UGX 20–30 million if needed.

# 10. Expected Outcomes

- National recognition for TISA as a leader in student innovation.

- At least 5 partnerships with government and private organizations.

- At least 30 teams participating from universities across Uganda.

- At least 3 solutions deployed with partner organizations.

- Internships and job opportunities for TISA members.

- Funding and in-kind support for TISA's long-term sustainability.

- A repeatable model for annual or biennial editions.

# 11. Risks and Mitigation

| Risk | Mitigation |
| --- | --- |
| Partners do not commit early | Start with anchor partners: UICT, ICT-Hub, one government body, one private company |
| Workload overwhelms the executive | Dedicated task force with clear roles; monthly reporting |
| Funding falls short | Design a minimal viable event first; scale with funding |
| Low student participation | Campus tours, social media campaign, TISA member incentives |
| Solutions are not deployed | Secure deployment commitments from partners before the event |

# 12. What We Are Asking From the Executive Board

- Approval in principle to proceed with planning.

- A mandate for the task force to approach partners on behalf of TISA.

- Formation of the task force as proposed in Section 6.

- A small initial budget (if available) for branding and partnership materials. Most costs will be covered by partners.

- Monthly reporting from the task force to the Executive Board.

# 13. Conclusion

# TISA has always been about turning bold ideas into real-world solutions. The TISA Inter-University ICT Challenge 2027 is our chance to do that at a national scale.

# This is not just another event. It is a statement that TISA is ready to lead, to partner, and to deliver. It is a legacy project that will benefit every member, every partner, and every community we touch.

# I request the Executive Board's approval to begin this journey.

# Prepared and submitted by:

# Aine Mbabazi Khuzaifah

# Vice President, TISA — UICT

# [Phone Number] | [Email]

# Date: [Insert Date]

# Next Steps After Approval

- Task force first meeting – within one week of approval.

- Assign roles and responsibilities – who does what.

- Create a shared workspace – Google Drive, WhatsApp group, or Notion.

- Draft the partnership proposal – for outreach to government and private sector.

- Begin partner outreach – start with UICT, ICT-Hub, and TISA's existing contacts.

- Set a date for the first progress report – one month from approval.